## High-Level Gantt
Gantt Chart (WBS 1.0 - 8.0)
WBS | Module | Owner | Start | Finish | Duration | 03-30 | 03-31 | 04-01 | 04-02 | 04-03 | 04-04 | 04-05 | 04-06 | 04-07 | 04-08 | 04-09 | 04-10 | 04-11 | 04-12 | 04-13 | 04-14 | 04-15 | 04-16 | 04-17 | 04-18 | 04-19 | 04-20 | 04-21 | 04-22 | 04-23 | 04-24 | 04-25 | 04-26 | 04-27 | 04-28 | 04-29 | 04-30 | 05-01 | 05-02 | 05-03 | 05-04 | 05-05 | 05-06 | 05-07 | 05-08 | 05-09 | 05-10 | 05-11 | 05-12 | 05-13 | 05-14 | 05-15 | 05-16 | 05-17 | 05-18 | 05-19 | 05-20 | 05-21 | 05-22 | 05-23 | 05-24 | 05-25 | 05-26 | 05-27 | 05-28 | 05-29 | 05-30 | 05-31 | 06-01 | 06-02 | 06-03 | 06-04 | 06-05 | 06-06 | 06-07 | 06-08 | 06-09 | 06-10 | 06-11 | 06-12 | 06-13 | 06-14
1.0 | Project Management | All members | 2026-03-30 | 2026-06-14 | 77d
2.0 | Requirements and System Design | All members | 2026-03-30 | 2026-04-12 | 14d
3.0 | Infrastructure and DevOps | 冯俊财 / 路清怡 | 2026-04-03 | 2026-04-12 | 10d
4.0 | Backend Development | 冯俊财 / 路清怡 | 2026-04-06 | 2026-05-17 | 42d
5.0 | Frontend Development | 张诗蔻 / 纪鹏 | 2026-04-13 | 2026-05-31 | 49d
6.0 | Platform Adaptation | 纪鹏 / 路清怡 | 2026-05-25 | 2026-05-31 | 7d
7.0 | Testing and QA | 纪鹏 / All members | 2026-05-27 | 2026-06-07 | 12d
8.0 | Documentation and Submission | 纪鹏 / All members | 2026-03-30 | 2026-06-14 | 77d
Milestones
ID | Milestone | Date
M1 | Foundation Ready | 2026-04-12 | [16 empty] | M1
M2 | Q&A MVP | 2026-04-26 | [30 empty] | M2
M3 | Teaching Loop Complete | 2026-05-17 | [51 empty] | M3
M4 | Full Feature Complete | 2026-05-31 | [65 empty] | M4
M5 | Project Delivery | 2026-06-14 | [79 empty] | M5
Legend | Critical Path | Normal Task | Weekend
Critical path used for presentation: 2.0 -> 3.0 -> 4.0 -> 5.0 -> 7.0 -> 8.0

## Milestones
Milestone | Description | Target Date
M1 | Foundation Ready: environment running; LLM API connected; database schema migrated; JWT auth verified; Celery/Redis and MinIO validated | 2026-04-12
M2 | Q&A MVP: course material upload, resource processing, and course-aware AI Q&A available (accuracy >= 90%) | 2026-04-26
M3 | Full teaching loop: submit assignment -> AI annotates -> learning analytics -> exercises generated | 2026-05-17
M4 | Full feature integration: platform embedding and Agent visual builder completed; Q&A >= 90%; grading >= 90% | 2026-05-31
M5 | System fully deployed on cloud server; end-to-end demo validated; project documentation complete | 2026-06-14